

# Background

The Cardiovascular Health Mission is investing $220 million over 10 years to improve cardiovascular health and stroke for all Australians under the Medical Research Future Fund (MRFF). The mission will improve health and save lives by mobilising research efforts, and developing collaborative and translational platforms. It will encompass broad innovations in cardiovascular health and stroke to benefit all Australians, with focused efforts to improve equity and outcomes for Aboriginal and/or Torres Strait Islander people. It was created in consultation with international experts to identify the key areas of research that will have the greatest impact on improving cardiovascular health for our future.

This plan supports the implementation of the Cardiovascular Health Mission roadmap and establishes a strategic plan to address the mission’s goals within the context of the MRFF 10-year plan. This implementation plan should be read in the context of the mission roadmap, which describes the mission’s scope, goals and principles.

# Overview

To target activities to achieve the objectives of the mission within the 10-year plan, a number of aims and priority areas for research investment have been identified. The following aims and priority areas have been identified as the key areas that could drive transformative improvements in cardiovascular disease and stroke outcomes for all Australians, including priority populations.

| Aim | Priority areas for investment |
| --- | --- |
| 1. Reduce the number of Australians of all ages affected by heart disease and stroke | 1.1 Improving understanding of cardiovascular disease risk, including biological mechanisms |
| 1.2 Identifying best-practice preventive care for all Australians through novel diagnostic, therapeutic and health service delivery strategies |
| 2. Improve outcomes from acute cardiovascular and stroke events | 2.1 Optimising evidence-based diagnoses and clinical pathways |
| 2.2 Discovering new solutions through innovation — technology, drugs and devices, and models of care |
| 3. Improve long-term recovery and survivorship after a cardiovascular or stroke event | 3.1 Identifying and targeting personalised lifelong care approaches, to prevent further stroke or heart events |
| 3.2 Developing new treatments for recovery with better understanding of the biology of recovery, leading to improved monitoring and new treatments |
| 3.3 Improving survivorship and reducing morbidity |

# Implementation strategy

The implementation strategy has been developed to guide research investment over the life of the mission. Investment aims to build capability and knowledge, as well as facilitate translation of advancements to clinical practice, to achieve the mission’s objectives. Support for exploratory and discovery projects in both the short and long term will be integral to the mission’s success. The implementation strategy is intended to make the research purpose and direction transparent and provide certainty to stakeholders. It also establishes how the outcomes of each focus area will be evaluated in terms of benefit to Australian patients, which will help to clarify the intended outcome and facilitate tracking of the mission’s progress towards its objectives.

Research activities will be, or contribute to, large programs of work of national strategic importance that are informed by the key priority areas outlined in this implementation plan. They are expected to be balanced across the critical areas of health. The research activities are also expected to foster collaboration and harness resources across the system to deliver improved health outcomes for Australians.

Important considerations that will factor into the mission’s implementation include:

prioritising equity considerations for all mission projects, including gender and social equity

developing best-practice methods for co-design and conduct, in partnership with end users, with consideration for all population groups across Australia and their needs

ensuring consumer and end-user involvement across all mission activities

including Aboriginal and/or Torres Strait Islander people to co-design and lead research activities

ensuring implementation of best practice is embedded across all mission activities

ensuring that funding is not directed to areas that will duplicate research (large or small studies) already being undertaken in Australia or overseas

Priority areas for investment are allocated across short, medium and long-term timeframes.

The [MRFF Monitoring, evaluation and learning strategy](https://www.health.gov.au/resources/publications/mrff-monitoring-evaluation-and-learning-strategy-2020-21-to-2023-24) (the Strategy) provides an overarching framework for assessing the performance of the MRFF, focused on individual grants, grant opportunities, initiatives (eg the Cardiovascular Health Mission) and the entire program. The Strategy sets out the principles and approach used to monitor and evaluate the MRFF. It outlines the need for evaluations to be independent and impartial. The Strategy aims to be transparent in process and outcomes, and agile to the needs of the MRFF, its consumers and stakeholders (such as the health and medical research industry).

The Cardiovascular Health Mission and grants funded under this initiative will be evaluated against the Strategy following three years of disbursements. Following this review, based on the outcomes, consideration will be given to whether priority areas for investment need to be modified or new ones identified.

## Cardiovascular Health Mission enablers

For each aim and priority area for investment, the implementation plan identifies non-research activities required to facilitate and support the MRFF-funded research and long-term implementation.

The following enablers will provide overarching support for the Cardiovascular Health Mission’s implementation:

* A nationally coordinated approach that leverages core research capabilities to support all funded projects to
* drive activity and outcomes, including embedding these outcomes into the health system
* coordinate aligned projects

develop, curate and manage a dataset for future research use

Effective and extensive engagement across all levels of government will be established to ensure the outcomes of the mission transform health care

Effectively use and link allied groups — including foundations, alliances and networks — to coordinate efforts and avoid duplication, to improve the mission’s impact

The mission enabling capabilities can also deliver:

Workforce development in areas such as large-scale bioinformatics, data analysis, data management and interpretation

Improved integration of data and research into continuous quality improvement

Improved integration with health system priorities, including health care quality standards, patient outcomes, economics, and financial factors and obligations

* Industry engagement, to
* accelerate the delivery of evidence-based and value-based health care

translate innovation into more effective treatments and patient management support tools, to support better patient, commercial and economic outcomes

collaboration nationally and internationally to maximise investments and research efforts, and reduce duplication

implementation research and health service engagement to realise the health benefits from innovation

A significant enabler for the Cardiovascular Health Mission is the Targeted Translation Research Accelerator, a $47 million program over four years that focuses on accelerating research into preventing, diagnosing and treating diabetes and cardiovascular disease. The accelerator will:

establish two research centres through competitive processes — one for diabetes and one for cardiovascular disease — to accelerate therapies for the prevention, early detection and treatment of disease-related complications

support through competitive processes research projects on the potential common pathways interactions and complexities for patients experiencing two or more of the following: type 1 diabetes, type 2 diabetes and cardiovascular disease

target investment and related support through partnership projects to progress promising drug and device development projects, with a focus on promoting commercialisation of novel therapeutics and devices for diabetes and cardiovascular disease

source, nurture and invest in early-stage therapeutic research targets to transform diagnostic and therapeutic care for people with diabetes

commission and conduct research to support the health and commercial sectors to deliver transformations in diabetes and cardiovascular disease

The Cardiovascular Health Mission will also actively pursue opportunities of collaboration with other MRFF initiatives and missions.

# Aim 1: Reduce the number of Australians of all ages affected by heart disease and stroke

## Priority area 1.1

Improving understanding of cardiovascular disease risk, including biological mechanisms

| Research to begin in the … | Priorities for investment (research questions and objectives) |
| --- | --- |
| short term (1–2 years) | Future research projects will:* enable better understanding of the mechanistic basis/pathophysiology of how non-cardiovascular diseases confer cardiovascular risk
* develop novel blood, imaging and clinical markers and methods for improved risk prediction and early detection of cardiovascular disease and stroke
* identify and quantify system and individual mechanisms that contribute to variation and inequities in cardiovascular disease and stroke care, and risk management, particularly in Aboriginal and/or Torres Strait Islander people
* use implementation- and systems-based research (built on principles of co-design methodology) to better understand and predict cardiovascular disease and stroke risk in Aboriginal and/or Torres Strait Islander people
 |
| medium term (2–5 years) to long term (6–10 years) | Research projects will:* identify and evaluate novel diagnostic markers and methods to better predict risk of cardiovascular disease and stroke
* develop and evaluate clinical pathways for implementing optimised evidence-based diagnosis and treatment
* support integration of individual and population approaches to optimise cardiovascular disease and stroke prevention
* better understand the mechanistic basis of how chronic diseases contribute to cardiovascular disease and stroke, and develop models to include this in risk prediction and prevention strategies
 |

### Opportunities to use additional investment and other research to support the priority areas include, but are not limited to, the following

* Partnerships may include:
* existing large-scale national and state data linkage systems (eg National Integrated Health Services Information, Multi-Agency Data Integration Project), and primary care data linkage systems to develop large-scale cardiovascular data platform integrating clinical, state, national and other data sources
* commercial clinical software providers to develop partnerships that support creating data aggregation platforms that the research sector can access
* private health insurers — for example, with the shared goal of value-based care and prevention
* the National Critical Research Infrastructure Strategy
* the Australian Health Research Alliance and the Australian Clinical Trials Alliance

the Heart Foundation and the Stroke Foundation to enable consumer engagement and advocacy relating to data security and big-data value

Use existing clinical registries and cohorts with biobanks to create national online open access resource. For example, there are data from 47,000 patients in individual cohorts from the Australian Cardiovascular Alliance Precision Medicine Flagship, and the Australian STROKE registry has data from more than 100,000 stroke patients

* Collaborative research with other MRFF missions including:
* Genomics Health Futures Mission — polygenic risk, and opportunities for co-funded grants
* Million Minds Mental Health Research Mission — co-funding towards preventive strategies in patients with mental illness

Indigenous Health Research Fund — support research to improve outcomes for Aboriginal and/or Torres Strait Islander people

Consultation and engagement on clinical guideline, and pathway implementation and infrastructure (eg the Cardiac Society of Australia and New Zealand, the Heart Foundation, the Stroke Foundation, the Royal Australian College of General Practitioners)

Leverage funding by incentivising sustainable partnerships with commercial diagnostic companies, and international collaborations with world-class facilities in precision cardiovascular health (eg Broad Institute, UK Biobank)

### Activities required to support the research and facilitate long-term implementation include, but are not limited to, the following

Create large-scale platforms, and integrate data linkage, national biobanks, imaging and online bioresources

Broad engagement of research, health and industry experts towards goals, to progress grants and present platforms

Clinical trials network contributing to large-scale national cohort studies (work with the Australian Health Research Alliance and the Australian Clinical Trials Alliance)

Advocate to consumers regarding data security, and benefits of large-scale data research

Undertake economic evaluations and impact assessments of new pathways and innovations in prevention

## Priority area 1.2

Identifying best-practice preventive care for all Australians

| Research to begin in the … | Priorities for investment (research questions and objectives) |
| --- | --- |
| short term (1–2 years) | Research to support effective adoption of and adherence to preventive health interventions for cardiovascular disease and stroke, including to:* identify the key barriers and enablers for adopting best-practice care across the care continuum
* identify effective community-based approaches
* address barriers to best-practice prevention for Aboriginal and/or Torres Strait Islander people, using co-design and culturally secure approaches

Develop novel interventions, including therapeutics and devices, to prevent cardiovascular disease and stroke, including identifying novel interventions that target individuals with chronic diseases contributing to cardiovascular disease and stroke and who experience rapid progression of disease despite best-practice care. |
| medium term (2–5 years) to long term (6–10 years) | Reduce the number of Australians experiencing cardiovascular disease and stroke by developing and implementing early, more effective preventive health interventions, including:* developing, optimising and implementing clinical pathways that embed evidence-based treatment, including for risk factors
* co-designing and developing strategies with Aboriginal and/or Torres Strait Islander people to embed best-practice, culturally secure cardiovascular disease and stroke prevention for Aboriginal and/or Torres Strait Islander people into care
* developing and implementing novel
* therapeutics/technologies for the prevention of cardiac disease caused by chronic diseases
* discoveries and markers to improve risk prediction
* approaches to tailor preventive care, support adherence and reduce inequalities
* trialling
* therapies that prevent cardiovascular disease and stroke associated with chronic disease
* novel interventions (individual and population level), including care pathways, integrated/multimodal solutions and biomarkers
* repurposed treatments and therapeutics, or new integrated models of care
 |

### Opportunities to use additional investment and other research to support the priority areas include, but are not limited to, the following

* Partnerships with
* commercial clinical software providers, to support creating data aggregation platforms that the research sector can access
* industry, universities and other organisations to support large-scale clinical trials, as well as early-phase drugs (eg through Australian Cardiovascular Alliance Industry members)
* the Department of Industry, Science, Energy and Resources, and state/territory departments
* the Digital Cooperative Research Centre and industry partners regarding new technology for personalised prevention
* private health insurers; for example, with the shared goal of value-based care and prevention
* the Royal Australian College of General Practitioners, primary care nurses and allied health, including pharmacists and exercise physiologists

the Heart Foundation, the Stroke Foundation, and other nongovernment organisations

National data platform integrating routinely collected large-scale national and state data linkage systems (eg National Integrated Health Services Information, Multi-Agency Data Integration Project), primary care data-linkage systems, hospital-based clinical quality registries and electronic health care records

Use advances in data to drive existing and novel clinical quality improvement processes

Clinical cardiovascular disease and stroke registries (innovative design with virtual population of data, and dashboard quality assurance and opportunity for clinical decision support)

Coordinated strong cardiovascular research community (eg Australian Cardiovascular Alliance, centres of research excellence)

Embed research outputs into health service initiatives using evidence-based knowledge translation methods to improve implementation, sustainability and health outcomes

National and state health departments, to advise on evidence- and value-based care to accelerate implementation and impact

### Activities required to support the research and facilitate long-term implementation include, but are not limited to, the following

Establish and consolidate partnerships with health services providers, consumers and policy makers for translation and implementation

Embedding clinical trials teams in the Australian Health Research Alliance and primary care network, with efficient innovative systems (eg in virtual registries)

Collaborate with the Indigenous Health Research Fund and experts on initiatives that increase engagement with the community and researchers, and drive towards equitable access and outcomes

Workforce development in clinical and large-scale data analysis, management and interpretation

Engage with industry, health and consumer partners to promote Australian intellectual property and build commercialisation capacity

Software development facilitating clinical implementation, including a national database of cardiovascular disease and stroke intellectual property (similar to the Stanford Office of Technology and Licensing; [techfinder.stanford.edu](http://techfinder.stanford.edu/))

Health economic and impact assessments

## Evaluation approach and measures

Improved cardiovascular health

New discoveries and biomarkers that improve prediction of cardiovascular disease and stroke are identified and available in clinical practice nationally

New clinical pathways with optimised treatments are identified and available in clinical practice nationally

A greater proportion of the eligible population having their cardiovascular and stroke risk assessed

A greater proportion of those at risk of cardiovascular disease and stroke receiving best-practice preventive care

Preventive approaches focused on individuals and communities available and implemented nationally

Inequalities in cardiovascular disease and stroke outcomes reduced for at risk populations, particularly Aboriginal and/or Torres Strait Islander people

Efforts to understand the potential return on investment and the health economic implications of the research

# Aim 2: Improve outcomes from acute cardiovascular and stroke events

## Priority area 2.1

Optimising evidence-based diagnoses and clinical pathways

| Research to begin in the … | Priorities for investment (research questions and objectives) |
| --- | --- |
| short term (1–2 years) | Research that accelerates equitable patient access to best care that results in best possible outcomes, including through:* novel technologies or devices to enhance and accelerate diagnosis, including outside of acute health settings
* identifying new biomarkers to support prognosis and treatment pathways
* improved identification and management of Aboriginal and/or Torres Strait Islander people with critical, time-dependent events
* novel approaches to better understand and quantify access to care, including drivers of inequalities to support targeted interventions
 |
| medium term (2–5 years) to long term (6–10 years) | Research to support adoption of novel and effective interventions and treatments, including reducing care inequities through:* developing, optimising and implementing clinical pathways that embed evidence-based treatment
* co-designing and developing strategies with Aboriginal and/or Torres Strait Islander people to embed best-practice, culturally secure cardiovascular disease and stroke prevention for Aboriginal and/or Torres Strait Islander people into care
* trialling novel diagnostic and prognostic tools
* trialling novel interventions, including technologies, digital health, and individual and population-based approaches

Research to foster uptake of best-practice care, including to reduce care inequities by:* improving translation of new evidence into practice
* improving uptake of evidence generated from the program into acute care guidelines or policy
 |

### Opportunities to use additional investment and other research to support the priority areas include, but are not limited to, the following

* Engagement with organisations involved in the adoption of novel and effective interventions and treatments, including:
* Australian Cardiovascular Alliance, the research community and flagship programs (precision medicine, bioengineering, big data, clinical trials, and implementation and policy), as well as industry and health partners
* Bioplatforms Australia, national imaging facilities and other National Collaborative Research Infrastructure Strategy organisations
* state health and ambulance services
* sporting and lifesaving organisations
* professional bodies, including the Cardiac Society of Australia and New Zealand, the Royal Australasian College of Physicians, the Royal Australian College of General Practitioners, the Australian and New Zealand Association of Neurologists
* industry partners
* Australian Health Research Alliance and the Royal Australian College of General Practitioners, to embed innovations in health care

the Heart Foundation and the Stroke Foundation — where feasible, matched funding, promoting implementation and evaluation

### Activities required to support the research and facilitate long-term implementation include, but are not limited to, the following

Encourage states and territories to implement dashboard of performance (best care and best outcomes)

Consumer and end user education and engagement regarding priorities informed by data

Whole-of-nation big data platforms for near real-time registries and to facilitate embedded clinical trials

Embed clinical trial networks in Australian Health Research Translation Centre networks as a platform to attract global pharmaceutical and device/technology partnerships, and accelerate Australian discovery and innovation

Encourage engagement with the broad research community

Early and ongoing engagement with relevant state departments of health, and with national bodies, including the Medical Services Advisory Committee and the Pharmaceutical Benefits Advisory Committee to support development and implementation of new technologies and devices

Engage clinical researchers to undertake research or contribute to research, with career development and mentorship

## Priority area 2.2

Discovering new solutions through innovation — technology, drugs and devices, and models of care

| Research to begin in the … | Priorities for investment (research questions and objectives) |
| --- | --- |
| short term (1–2 years) | Develop novel treatments and devices to improve outcomes (eg reduce complications, length of stay) following acute cardiovascular and stroke events, including:* identifying novel molecular targets through an understanding of the pathophysiology of disease
* repurposing existing drug therapies and/or developing new combinations of drugs
* developing novel devices, technologies and systems
* identifying specific solutions for individuals who experience rapid progression in disease despite receiving the best evidence-based care
* identifying the molecular and pathophysiological causes of rapid progression in disease so that solutions can be developed
 |
| medium term (2–5 years) to long term (6–10 years) | Research to support adoption of novel and effective interventions and treatments, including:* developing, optimising and implementing models of care that embed evidence-based treatment
* trialling novel devices, technologies and systems of care
* trialling novel and repurposed therapeutics and treatments
* addressing inequalities in access and outcomes

Preclinical development and validation of novel molecular targets and novel device approaches.Phase 1 and Phase 2 clinical trials to demonstrate safety and potential efficacy of novel devices and therapeutic approaches. |

### Opportunities to use additional investment and other research to support the priority areas include, but are not limited to, the following

Engage with industry partners to repurpose existing products for diseases or subgroups with an identified gap in treatment options

Attract global pharmaceutical and device companies to Australia for clinical trials across phases 1–3

Collaboration with local biotechnology/medical technology companies to accelerate development and validation of their technologies

Engage the Australian Cardiovascular Alliance platform for interdisciplinary research in drug discovery, bioengineering, clinical trials, implementation and policy, as well as industry and commercialisation

The Australian Clinical Trials Alliance, the Cardiac Society of Australia and New Zealand, the Stroke Society of Australasia, the Heart Foundation, the Stroke Foundation for clinical expertise about pathway and guideline development

### Activities required to support the research and facilitate long-term implementation include, but are not limited to, the following

Coordination of multidisciplinary research and clinical teams

Access to infrastructure — for example, through the National Collaborative Research Infrastructure Strategy

Phase 1 device network, with preclinical arm (bringing in global investment and providing a platform for local innovation)

Clinical trials network across the Australian Health Research Alliance, supported by the Australian Clinical Trials Alliance

Data platforms to measure impact and continually assess gaps

Early and ongoing engagement with state departments to support uptake of evidence and value-based priorities for implementation

Undertake impact assessments, while considering health, economic and social value measures

Investment in biotechnology, including incentivising global industry investment in Australia

## Evaluation approach and measures

New discoveries and biomarkers that improve diagnosis and prognostication of cardiovascular disease and stroke are identified and available in clinical practice nationally

New clinical pathways with optimised treatments are identified and available in clinical practice nationally

Novel interventions, treatments and devices are developed and available in clinical practice nationally

A greater proportion of those experiencing cardiovascular disease and stroke receiving best practice acute care

Improved access to the most appropriate care, including reducing care inequalities in cardiovascular disease and stroke outcomes for at-risk populations, particularly Aboriginal and/or Torres Strait Islander people

# Aim 3: Improve long-term recovery and survivorship after a cardiovascular or stroke event

## Priority area 3.1

Identifying and targeting personalised lifelong care approaches, to prevent further stroke or heart events

| Research to begin in the … | Priorities for investment (research questions and objectives) |
| --- | --- |
| short term (1–2 years) | In the short to medium term, small-scale development projects will establish feasible, evidence-based approaches for:* new models (eg digital/bioengineering) that can increase treatment adherence and engagement for all heart and stroke survivors undergoing current best-evidence treatments (drugs, lifestyle)
* new, more effective approaches specifically for Aboriginal and/or Torres Strait Islander people, including co-design and culturally secure approaches
* approaches that incorporate health system monitoring, consumer feedback and policy change to increase participation and improve health outcomes
 |
| medium term (2–5 years) to long term (6–10 years) | Large-scale project focused on discovery and testing of new, broadly applicable (multiple disease groups) interventions (eg anti-inflammatory targets)Research projects or next-phase studies, which may include:* promising models that improve adherence to best-practice care
* new, more effective approaches specifically for Aboriginal and/or Torres Strait Islander people, including co-design and culturally secure approaches
* approaches that incorporate health system monitoring, consumer feedback and policy change to increase participation and improve health outcomes

Research to support adoption of evidence-based approaches:* for adherence/engagement for all heart and stroke survivors undergoing current best-evidence treatments (drugs, lifestyle), such as digital, bioengineering approaches
* for Aboriginal and/or Torres Strait Islander people including co-design and culturally secure approaches
* that incorporate health system monitoring, consumer feedback and policy change to increase participation and improve health outcomes
 |

### Opportunities to use additional investment and other research to support the priority areas include, but are not limited to, the following

Engagement with venture capitalists, national and state governments, commercial partners, consumers, community organisations, philanthropic organisations, universities, professional bodies and international partners to provide opportunities for Australia to lead the world in developing new treatment pipelines for drugs, biodevices, digital health technology, creating industry–academic partnerships and investment

Registry-based clinical trials and consumer-relationship management platforms to quickly and effectively communicate with potential users of new and existing products and services

Engage the Australian Cardiovascular Alliance research community (includes more than 1000 broader research, industry and health communities)

### Activities required to support the research and facilitate long-term implementation include, but are not limited to, the following

Development of a mechanism for overseeing or identifying linkages between and across bodies of funded work in the mission(s), enabling outcomes to be optimised

Establish linkages with resources/entities to help build business cases for commercialisation to maximise co-investment opportunities

Engage with state departments to encourage collaborative approaches and agree to policy/data initiatives that are generated from this work

## Priority area 3.2

Developing new treatments for recovery with better understanding of the biology of recovery, leading to improved monitoring and new treatments

| Research to begin in the … | Priorities for investment (research questions and objectives) |
| --- | --- |
| short term (1–2 years) | In the short term, small-scale development projects will establish feasible, evidence-based approaches for:* the discovery and validation of new molecular targets and new device approaches for treatment, and to improve recovery
* new therapeutics, including drugs and devices that improve the function of the heart and brain, including target validation to improve functional recovery and survivorship
* health informatics approaches that use artificial intelligence and machine learning to help patient selection for trials, optimise targeting of treatments and patient outcomes
 |
| medium term (2–5 years) to long term (6–10 years) | Research to discover and develop new therapeutic and device strategies to improve heart and brain function for better recovery, which may include:* clinical trials of novel therapeutics, devices and technologies
* new biomarkers or more effective diagnostics
* trialling repurposed drugs or combinations thereof

Research to understand recovery trajectories and phenotypes, which may include:* trial network or big data system enhancements that accelerate patient selection, and recruiting and testing novel treatments
* developing and testing novel outcome assessment tools or biomarkers of recovery

A large-scale multiomics project focused on improving understanding of recovery trajectories and phenotypes, underpinning recovery and survivorship in cardiovascular disease and stroke.Research to embed systems for tracking long-term recovery (with novel biomarkers, outcome assessment) in cardiovascular disease and stroke. |

### Opportunities to use additional investment and other research to support the priority areas include, but are not limited to, the following

Consumer engagement, community organisations, universities, incubator and seed funds, biotechnology and medical technology companies, pharmaceutical companies and international partners

Coordinated efforts for productive use of funds to develop systems that work across multiple conditions

* Partnerships with:
* digital innovation companies about the best approach for data format and interrogation, and collaboration; and intellectual property generation for small and medium enterprises, pharmaceutical and device industries, and local technology industries
* Australian Cardiovascular Alliance for research community engagement (more than 1000 researchers, industry and health care providers, beyond the grant teams), working towards prioritised goals

pharmaceutical and device companies to attract international Phase 1 to Phase 3 studies, and build an ecosystem for industry–academic partnership across the pipeline

Engagement with venture capitalists, national and state governments, commercial partners, consumers, community organisations, philanthropic organisations, universities, professional bodies and international partners to provide opportunities for Australia to lead the world in developing new treatment pipelines for drugs, biodevices and digital health technology, creating industry–academic partnerships and investment

The Australian Government’s 2030 Innovation Plan aims for Australia to be a leading nation in artificial intelligence and machine learning

### Activities required to support the research and facilitate long-term implementation include, but are not limited to, the following

Facilitate collaboration among those who are working in the same area to encourage linkages between groups

Engage with leading national cardiovascular (heart and stroke) research alliances to accelerate this work

Partnership opportunities with pharmaceutical companies in trial networks

Identify pharmaceutical requirements for the most effective partnerships, so that value within Australia is maximised while taking advantage of global pharmaceutical company resources and networks

Coordination and collaboration between proposed systems to stream patients into trials

Broad partnerships and networks of people with data and analytics expertise

Liaise closely with Australian industry and commercialisation partners

Encourage feeding information from clinical trial learnings into big data platforms to enhance development of precision medicine for heart and stroke

## Priority area 3.3

Improving survivorship and reducing morbidity

| Research to begin in the … | Priorities for investment (research questions and objectives) |
| --- | --- |
| short term (1–2 years) | In the short term, small-scale development projects will establish feasible, evidence-based approaches for:* new models of rehabilitation and recovery support that increase survival and quality of life
* initiatives that increase equity of access for all people (eg digital or online delivery of services like tele-rehab for heart and stroke)
* new, efficient models that respond to survivor needs, and that deliver routine, annual checking and monitoring of people with heart and stroke problems to improve outcome and survivorship
* new, innovative models that improve treatment adherence by empowering survivors to more effectively manage their recovery, through co-design with survivors
* new, culturally secure models to improve treatment adherence by empowering Aboriginal and/or Torres Strait Islander people, through co-design
 |
| medium term (2–5 years) to long term (6–10 years) | A large-scale project that builds on the development projects that are focused on:* new models of rehabilitation and recovery support that increase equity of access for all people (eg digital or online delivery of services like tele-rehab for heart and stroke)
* new, efficient models that respond to survivor needs, and that deliver routine, annual checking and monitoring of people with heart and stroke problems to improve outcome and survivorship
* new, innovative models that improve treatment adherence by empowering survivors to more effectively manage their recovery, through co-design with survivors
* new, culturally secure models to improve treatment adherence by empowering Aboriginal and/or Torres Strait Islander people, through co-design

Research to support effective national adoption and best-practice use of rehabilitation and recovery programs. |

### Opportunities to use additional investment and other research to support the priority areas include, but are not limited to, the following

* Partnerships with:
* data mining and artificial intelligence companies

industry (eg data analytics)

Engagement with consumer, community organisations, universities, international partners and businesses (eg gyms, information technology companies)

Venture capital funding

Collaborations with national and state governments, and consumer organisations

* Leveraging:
* existing support systems and programs for maximum effect

policies, practices, standards and systems from existing well-established, national databanks

### Activities required to support the research and facilitate long-term implementation include, but are not limited to, the following

Facilitate collaboration among those who are working in the same area to encourage linkages between groups

A national cardiovascular (heart and stroke) disease platform would significantly accelerate this work

Encourage applicants to identify training opportunities for early career researchers within the project

Identify funding strategies that support career development and sustainability

Consider and implement data security

## Evaluation approach and measures

New treatments and interventions that improve outcomes following cardiovascular disease and stroke are identified and available in clinical practice nationally

A greater proportion of people have access to effective rehabilitation following cardiovascular disease and stroke

Inequality in access to rehabilitation for at-risk groups reduced, particularly for Aboriginal and/or Torres Strait Islander people