Action Plan for Aged Care Data and
Digital Strategy 2024–2029

Acknowledgements

The Department of Health and Aged Care gratefully acknowledges the advice, input and support of the many organisations and individuals who contributed to developing this document through user research, engagement and consultation processes.

The Department of Health and Aged Care recognises Aboriginal and Torres Strait Islander peoples as the First Peoples of this nation. The Commonwealth recognises the ongoing traditional and modern cultural practices and connection to Country held by Aboriginal and Torres Strait Islander peoples. The Commonwealth acknowledges Elders past, present and emerging as the Traditional Custodians and Lore Keepers of the world’s oldest living culture.

Copyright

© 2024 Commonwealth of Australia as represented by the Department of Health and Aged Care

This work is copyright. You may copy, print, download, display and reproduce the whole or part of this work in unaltered form for your own personal use or, if you are part of an organisation, for internal use within your organisation, but only if you or your organisation:

(a) do not use the copy or reproduction for any commercial purpose; and

(b) retain this copyright notice and all disclaimer notices as part of that copy or reproduction.

Apart from rights as permitted by the Copyright Act 1968 (Cth) or allowed by this copyright notice, all other rights are reserved, including (but not limited to) all commercial rights.

Requests and inquiries concerning reproduction and other rights to use are to be sent to the Communication Branch, Department of Health and Aged Care, GPO Box 9848, Canberra ACT 2601, or via e-mail to copyright@health.gov.au.

Creative Commons Licence

This publication is licensed under the Creative Commons Attribution 4.0 International Public License available from. (<http://creativecommons.org/licenses/by/4.0/legalcode>). (“Licence”). You must read and understand the Licence before using any material from this publication.

Restrictions

The Licence may not give you all the permissions necessary for your intended use. For example, other rights (such as publicity, privacy and moral rights) may limit how you use the material found in this publication.

The Licence does not cover, and there is no permission given for, use of any of the following material found in this publication:

* the Commonwealth Coat of Arms. (by way of information, the terms under which the Coat of Arms may be used can be found on the Department of Prime Minister and Cabinet website http://www.dpmc.gov.au/government/commonwealth-coat-arms)
* any logos and trademarks
* any photographs and images
* any signatures; and
* any material belonging to third parties.

Attribution

Without limiting your obligations under the Licence, the Department of Health and Aged Care requests that you attribute this publication in your work. Any reasonable form of words may be used provided that you:

* include a reference to this publication and where, practicable, the relevant page numbers;
* make it clear that you have permission to use the material under the Creative Commons Attribution 4.0 International Public License;
* make it clear whether or not you have changed the material used from this publication;
* include a copyright notice in relation to the material used. In the case of no change to the material, the words “© Commonwealth of Australia (Department of Health and Aged Care) 2024” may be used. In the case where the material has been changed or adapted, the words: “Based on Commonwealth of Australia (Department of Health and Aged Care) material” may be used; and
* do not suggest that the Department of Health and Aged Care endorses you or your use of the material.

Enquiries

Enquiries regarding any other use of this publication should be addressed to the Branch Manager, Communication Branch, Department of Health and Aged Care, GPO Box 9848, Canberra ACT 2601, or via e-mail to copyright@health.gov.au.

Table of contents

[A tangible plan for improving data and digital in aged care 4](#_Toc170142494)

[Strategy on a page 5](#_Toc170142495)

[Our delivery partners 6](#_Toc170142496)

[Overview of our Action Plan 7](#_Toc170142497)

[Action plan and progress for outcome 1 9](#_Toc170142498)

[Action plan and progress for outcome 2 13](#_Toc170142499)

[Action plan and progress for outcome 3 18](#_Toc170142500)

[Action plan and progress for outcome 4 21](#_Toc170142501)

[Delivering and developing the Plan 25](#_Toc170142502)

[Indicators and rationales to monitor the Strategy 26](#_Toc170142503)

# A tangible plan for improving data and digital in aged care

This Action Plan (the Plan) underpins the Aged Care Data and Digital Strategy (the Strategy), outlining how the Department of Health and Aged Care and its partners will deliver the Strategy. Actions are presented under each priority and outcome, which will collectively achieve the Strategy’s vision.

Vision

To deliver the highest quality person-centred care for older people while driving a sustainable and productive care and support economy through data and digital innovation.

**Concrete actions outlined in this Plan will provide support to older people and their support networks, aged care workers, service providers and technology vendors.**

The Plan will be regularly reviewed and updated. Every year, a report will be made on the progress towards each of the outcomes. Updates will be given to show the actions planned for the next year and those that have been completed.

We've outlined a timeline for implementation:

* short-term horizon (2024-2026)
* medium-term horizon (2024-2027)
* long-term horizon (lifetime of the Strategy and beyond).

For each action, the Plan identifies:

* what we’re doing
* why are we doing it
* who will lead it
* who we’ll partner with
* when we’ll deliver.

We want to hear from you to identify the action areas that are most important to you and what is working. We also want to understand where we can increase our focus to create an aged care system that leverages data and digital technology to improve the care that older people receive.

# Strategy on a page

Vision

To deliver the highest quality person-centred care for older people while driving a sustainable and productive care and support economy through data and digital innovation.

Guiding principles

* Person-centred
* Tell us once
* Diverse
* Integrated
* Care-focused
* Trusted

Outcomes

* Outcome 1: Older people and their support networks can navigate and actively participate in their care and wellbeing.
* Outcome 2**:** Aged care workers, service providers and health professionals are digitally empowered to provide higher quality and better-connected care.
* Outcome 3**:** Data is shared and reused securely to deliver a sustainable and continually improving aged care system.
* Outcome 4**:** Modern data and digital foundations underpin a collaborative, standards-based care system.

Priorities

* Promote healthy ageing, independence and choice
* Create simplified, user-friendly experiences
* Maximise time for direct care
* Strengthen care connections
* Improve security and access control
* Optimise data collection and utilisation
* Build and embed data and digital maturity
* Encourage innovation and provide stewardship

Despite the Strategy’s digital focus, older people can still get aged care information and services in person or by phone if they prefer.

# Our delivery partners

The aged care system is complex and interconnected. Making real, tangible change means having deep partnerships with all parts of this system, and keeping older people at the centre.

The Strategy seeks to empower the aged care sector, enhance their digital maturity and foster care connections between the health and aged care systems. Successfully delivering this strategy requires input and collaboration with all aged care and health care stakeholders.

For each of the actions in the Plan, we have identified an owner, as well as the key delivery partners, who will help make them happen. These will not be the only people involved, as for all actions we want the thoughts, guidance and input from those it will affect most – older people and their support networks, our aged care workforce, service providers.

The diagram below illustrates our key stakeholders, and who we will proactively engage throughout the delivery of the Plan:



# Overview of our Action Plan

The below is a transcript of an infographic displaying each of the 4 strategy outcomes with its corresponding priorities, actions and status.

## Outcome 1:

Older people and their support networks can navigate and actively participate in their care and wellbeing.

* **Priority 1**: Promote healthy ageing, independence and choice
	+ **Actions:**
		- Healthy ageing support tool – LiveUp TM
			* Status: Work commenced
		- Digital and health literacy
			* Status: Implementation
		- Translation of emerging digital technology
			* Status: Implementation
* **Priority 2**: Create simplified, user-friendly experiences
	+ **Actions:**
		- My Aged Care enhancements
			* Status: Work commenced
		- Aged care digital design standards
			* Status: Planning

## Outcome 2:

Aged care workers, service providers and health professionals are digitally empowered to provide higher quality, and better-connected, care.

* **Priority 3:** Maximise time for direct care
	+ **Actions:**
		- Virtual nursing in aged care project
			* Status: Planning
		- e-Prescribing
			* Status: Implementation
		- Worker digital literacy
			* Status: Ongoing
		- Wellness and reablement support tool - KeepAbleTM
			* Status: Work commenced
		- Integrated Assessment Tool application
			* Status: Work commenced
* **Priority 4:** Strengthen care connections
	+ **Actions:**
		- My Aged Care to My Health Record integration
			* Status: Work commenced
		- Aged Care Transfer Summary
			* Status: Ongoing

## Outcome 3:

Data is shared and reused securely to deliver a sustainable and continually improving aged care system.

* **Priority 5:** Improve security and access control
	+ **Actions:**
		- Aged care data governance framework
			* Status: Planning
* **Priority 6:** Optimise data collection and utilisation
	+ **Actions:**
		- Government Provider Management System
			* Status: Ongoing
		- Aged Care National Minimum Data Set
			* Status: Implementation
		- National Aged Care Data Asset
			* Status: Implementation
		- Aged Care Clinical Information System Standards
			* Status: Work commenced

## Outcome 4:

Modern data and digital foundations underpin a collaborative, standards-based care system.

* **Priority 7:** Build and embed data and digital maturity
	+ **Actions:**
		- Business to Government connectivity
			* Status: Ongoing
		- Discovery into provider digital adoption and uplift
			* Status: Planning
		- Interoperability and reference architecture
			* Status: Planning
* **Priority 8:** Encourage innovation and provide stewardship
	+ **Actions:**
		- AI and innovation frameworks
			* Status: Planning
		- AI technology pilots in aged care
			* Status: Planning
		- Virtual reality trials in aged care
			* Status: Planning

# Action plan and progress for outcome 1

**Older people and their support networks can navigate and actively participate in their care and wellbeing.**

Progress on this outcome means making data and digital technology more accessible and useful. This supports people to better understand and make informed choices about their care.

## Description of the priority areas to achieve this outcome:

Priority 1: Promote healthy ageing, independence and choice

This is about using digital tools and data to help older people, whether they are currently using aged care services or not, to:

* understand their own ageing
* what help is available
* age healthily
* make decisions about their own care.

It seeks to foster an environment in which older people are:

* given choices about their care delivery
* empowered with culturally safe and appropriate tools and information to make those decisions
* shown ways they can easily transition into aged care when they need to.

Priority 2: Create simplified, user- friendly experiences

This priority centres on ensuring that all digital interactions are intuitive, accessible, and enriching for older people, support networks, aged care workers and service providers.

* It is beneficial to design technology with users in mind, ensuring easy input, streamlined experiences and relevance of information.
* It seeks to realise the potential of digital technology by making it more accessible, easy to navigate and understand, and driving increased confidence and adoption of technology.

## Actions linked to priorities and progress for outcome 1

### Priority 1: Promote healthy ageing, independence and choice

#### Healthy ageing support tool – LiveUp TM

LiveUp, an existing digital channel, will be strengthened and transformed so older people can easily get free information and resources on healthy ageing. This will include practical tips and tools on how to better manage aspects of the ageing journey.

* What we’re going to do:
	+ develop an evidence-based tool that people can use to understand where they are on their ageing journey
	+ use behavioural insights and form strategic partnerships to inform and expand Liveup
	+ in-person engagement with older people and their community networks
	+ expand our navigator team who provide individual support through phone, email, and online chat.
* Why we’re doing this:
	+ Early intervention, education and support can positively impact age-related decline.
* Who will lead it:
	+ Independent Living Assessment
* Who we’ll partner with:
	+ Peak bodies
	+ Research organisations
* Short-term horizon:
	+ work commenced

#### Digital and health literacy

We are working to improve digital and health literacy, including promoting the Be Connected program, which has successfully increased the confidence, skills and online safety of older people.

* What we’re going to do:
* continue the successful Be Connected program until 30 June 2028. This includes maintaining and promoting:
	+ the Be Connected website
	+ free access to in-person support and mentoring
* research into digital and health literacy to help with healthy ageing and groups more likely to be digitally excluded
* Why we’re doing this:
	+ Digital literacy is increasingly important for healthy ageing. While digital inclusion is improving across the nation, digital literacy of people aged over 65 remain well below the national average.
* Who will lead it:
	+ Department of Health and Aged Care
* Who we’ll partner with:
	+ Department of Social Services
	+ eSafety Commissioner
	+ Good Things Foundation
	+ Australian Digital Health Agency
* Short-term horizon:
	+ implementation

#### Translation of emerging digital technology

Emerging research and technology has resulted in a range of devices and applications being developed that could be used in aged care.

* What we’re going to do:
	+ support Aged Care Research and Industry Innovation Australia to facilitate the adoption of innovation and technology in aged care
	+ examine funding mechanisms to support the uptake of proven, effective solutions.
* Why we’re doing this:
	+ To harness research and innovation in technologies that can assist older people, workers and service providers to improve care and wellbeing.
* Who will lead it:
	+ Aged Care Research and Industry Innovation Australia
* Who we’ll partner with:
	+ Service providers
	+ Technology vendors
	+ Research organisations
* Medium-term horizon:
	+ implementation

### Priority 2: Creating simplified, user-friendly experiences

#### My Aged Care enhancements

Continue to improve the My Aged Care customer experience by enhancing access and navigation to information about aged care services.

* What we’re going to do:
	+ explore what users want and find ways to improve the find a provider tool to help people easily find the care they need
	+ review and update website content and tools to align with the new aged care act and related reforms, including:
	+ refundable accommodation deposit scheme
	+ single assessment system
	+ provider registration.
* Why we’re doing this:
	+ To improve the digital My Aged Care user experience and make it easier for older people and their support networks to access information to make informed choices about their care.
* Who will lead it:
	+ The Department of Health and Aged Care
* Who we’ll partner with:
	+ Aged Care Quality and Safety Commission
	+ My Aged Care delivery partners
	+ Service providers
* Short-term horizon:
	+ work commenced

#### Aged care digital design standards

Connect with ongoing work relating to digital design standards in health, building upon them and expanding them into aged care as necessary.

* What we’re going to do:
	+ work together with teams developing digital design standards in the Australian Digital Health Agency and throughout the department
	+ develop shared design principles and guidelines
	+ map out aged care specific requirements.
* Why we’re doing this:
	+ To provide clarity and consistency for technology vendors, providers and others in the sector who are developing and using digital solutions.
* Who will lead it:
	+ The Department of Health and Aged Care
* Who we’ll partner with:
	+ Australian Digital Health Agency
	+ Technology vendors and sector groups
	+ Research organisations
* Long-term horizon:
	+ Planning

# Action plan and progress for outcome 2

**Aged care workers, service providers and health professionals are digitally empowered to provide higher quality and better-connected care.**

This outcome focuses on increasing worker digital literacy and building and sustaining the digital maturity of service providers. It includes the establishment of data and digital solutions to connect care services and improve the quality and delivery of person-centred care.

## Description of the priority areas to achieve this outcome:

Priority 3: Maximise time for direct care

This priority is about using data and digital technology to optimise the use of time and resources, so more time can be dedicated to providing high-quality care for older people.

It aims to build organisational digital capabilities and digital skills of the workforce, so that less time is spent on non-care activities, including:

* duplicative data entry
* administration
* communication
* information collection.

Priority 4: Strengthen care connection

This priority seeks to:

* improve care coordination
* enhance treatment outcomes
* provide a more holistic and person-centred approach to care, recognising the complex needs of each person.

It aims to facilitate the seamless flow of information across:

* health
* aged care
* allied health
* other care sectors.

Its purpose is to create an integrated and connected care ecosystem, ensuring that relevant data can be shared securely and efficiently where needed. The story and information of an older person should flow seamlessly between health and aged care professionals, utilising treatment plans and ensuring timely interventions.

## Actions linked to priorities and progress for outcome 2

### Priority 3: Maximise time for direct care

#### Virtual nursing in aged care project

The project will support the development and testing of a framework for the delivery of safe and high-quality virtual nursing support in aged care.

* What we’re going to do:
	+ engage with stakeholders on the development of the framework and its implementation
	+ select virtual care service suppliers and residential aged care homes that are experiencing workforce challenges
	+ independently evaluate clinical outcomes, workforce and service sustainability.
* Why we’re doing this:
	+ To build evidence on how virtual care services can enhance the provision of high-quality care to older people living in residential aged care homes.
* Who will lead it:
	+ The Department of Health and Aged Care
* Who we’ll partner with:
	+ Nursing and First Nations peak bodies
	+ Digital health advisors
	+ Government agencies
	+ Aged Care Quality and Safety Commission
* Medium-term horizon:
	+ planning

#### e-Prescribing

An electronic prescription service will enhance clinical safety and medication practices and reduce administrative burden, particularly for workers in aged care.

* What we’re going to do:
	+ deliver a stable and sustainable prescription delivery service to support the uptake of electronic prescribing across aged care.
* Why we’re doing this:
	+ Maintain privacy and provide greater choice for older people, and support electronic medication charts in residential aged care homes.
* Who will lead it:
	+ The Department of Health and Aged Care
* Who we’ll partner with:
	+ Australian Digital Health Agency
	+ State and territory governments
	+ Technology vendors
	+ Department of Veterans’ Affairs
	+ Australian Commission on Safety and Quality in Health Care
	+ Professional and peak bodies
* Medium-term to long-term horizon:
	+ ongoing

#### Worker digital literacy

Under the Capability Action Plan, we are equipping workers for a digitally-enabled future with standard capability frameworks, guidelines, resources, and tools.

* What we’re going to do:
	+ pilot and evaluate the national digital health capability framework and self-assessment tool in residential aged care
	+ promote standardised digital health capabilities
	+ develop an online hub for workers and employers to access digital health information and resources.
* Why we’re doing this:
	+ To build digital capability in the workforce to meet older people’s needs now and in the increasingly digitally-enabled future.
* Who will lead it:
	+ The Department of Health and Aged Care
* Who we’ll partner with:
	+ Australasian Institute of Digital Health
	+ Australian Digital Health Agency
	+ Medical Software Industry Association
	+ Primary Health Networks
* Medium-term horizon:
	+ ongoing

#### Wellness and reablement support tool – KeepAbleTM

KeepAble, an existing digital channel, will be significantly strengthened. This will empower aged care workers, service providers and health professionals to access high-quality information to support older people to age well.

* What we’re going to do:
	+ develop an evidence-based tool that can be used easily in rehabilitation, respite, reablement and restorative care
	+ use a behavioural science framework to identify the optimal digital and non-digital delivery mechanisms
	+ accelerate content development of KeepAble by working collaboratively with stakeholders.
* Why we’re doing this:
	+ To provide workers and service providers with resources and training to encourage independence and healthy ageing for older people.
* Who will lead it:
	+ Independent Living Assessment
* Who we’ll partner with:
	+ Research organisations
	+ Service providers
	+ Peak bodies
* Short-term horizon:
	+ work commenced

#### Integrated Assessment Tool (IAT) application

The IAT application will enable the assessment workforce to collect more complete information and have the flexibility to record the individual story of each older person and their carers.

* What we’re going to do:
	+ develop, test, and launch an IAT application to replace the national aged care screening and assessment form
	+ create assessor training and user guides to support implementation
	+ update the assessment manual to reflect changes
	+ review and evaluate the application for future enhancements.
* Why we’re doing this:
	+ The application will make it easier to gather more complete information. This supports the principle of ‘Tell us Once’.
* Who will lead it:
	+ The Department of Health and Aged Care
* Who we’ll partner with:
	+ Aged care assessors
	+ Assessment management organisations
	+ Lean educator network
* Short-term horizon:
	+ implementation

### Priority 4: Strengthen care connections

#### My Aged Care to My Health Record integration

With an older person's consent, integrating Aged Care Support Plans into My Health Record will provide care team with more comprehensive information. This will enable quicker and better-informed decisions regarding their treatment.

* What we’re going to do:
	+ make aged care support plans available in My Health Record by authorised users
	+ update my aged care website to provide information to consumers about linking to My Health Record
	+ support My Health Record registration, connection and use in aged care.
* Why we’re doing this:
	+ Carers, and clinicians working in healthcare cannot easily access aged care information. Similarly, clinicians in aged care struggle to access information provided by those in healthcare. The lack of information-sharing means that older people could be repeating their stories, leading to inefficiencies and if things are missed, poorer health and wellbeing outcomes.
* Who will lead it:
	+ The Department of Health and Aged Care
* Who we’ll partner with:
	+ Australian Digital Health Agency
	+ Services Australia
* Medium-term horizon:
	+ work commenced

#### Aged Care Transfer Summary

The Aged Care Transfer Summary is a digital solution using My Health Record. It provides crucial health information about a person living in residential aged care. This information supports the transition of the resident from an aged care setting to acute hospital care when needed.

* What we’re going to do:
	+ partner with aged care software vendors to uplift clinical information system standards and eMMS products to become conformant with My Health Record and enable functionality.
* Why we’re doing this:
	+ Enable key health information to be made easily available and follow the older person when they move between residential aged care and acute care settings.
* Who will lead it:
	+ Australian Digital Health Agency
* Who we’ll partner with:
	+ Software industry
	+ Residential aged care homes
* Short-term horizon:
	+ ongoing

# Action plan and progress for outcome 3

**Data is shared and reused securely to deliver a sustainable and continually improving aged care system.**

Progress against this outcome involves optimising the collection and use of data, ensuring that only useful data is collected, that it is collected at the right place, and that it is used effectively to improve care.

## Description of the priority areas to achieve this outcome:

Priority 5: Improve security and access control

This priority aims to improve the provision and security of digital and data technology to ensure aged care information is secure and reliable. It seeks to provide access to data and systems only where there is a genuine and approved need, and never at the expense of the protection, privacy and security of data. By developing a culture utilising the improvement of security and access control, aged care data will be protected from emerging risks.

Priority 6: Enhance data collection and use

This priority focuses on using data and digital solutions to deliver high-quality, evidence-based care that is tailored to individuals and continuously improving. Improved access to relevant data allows aged care workers to make better-informed decisions, identify improvement areas, and use services for the best possible outcomes for older people.

The secondary use of data enables research, providing an evidence base for future decisions. Improving data access and usage in aged care transforms data into a powerful tool for continuous improvement and decision-making, ultimately leading to enhanced care and wellbeing for older people.

## Actions linked to priorities and progress for outcome 3

### Priority 5: Improve security and access control

#### Aged care data governance framework

Develop a new aged care data governance framework that will include data security, sharing and release measures designed to maximise interoperability while still protecting the privacy of individual information.

* What we’re going to do:
	+ consult and develop a governance framework that outlines roles, responsibilities and accountabilities across the aged care portfolio
	+ further strengthen cyber security of aged care data and digital infrastructure
	+ embed this framework across the department and aged care portfolio.
* Why we’re doing this:
	+ To create a modern and robust framework to manage, share and report on aged care data securely through its lifecycle.
* Who will lead it:
	+ The Department of Health and Aged Care
* Who we’ll partner with:
	+ Australian Institute of Health and Welfare
	+ Aged Care Safety and Quality Commission
	+ Australian Digital Health Agency
	+ Services Australia
* Short-term horizon:
	+ planning

### Priority 6: Enhance data collection and use

#### Government Provider Management System (GPMS)

GPMS makes it easier for service providers to self-manage, view and maintain their information in real time.

* What we’re going to do:
	+ provide a master source of aged care provider information
	+ allow for future development of a whole-of-government provider management system
	+ replace legacy ICT infrastructure with a contemporary and extensible platform to support future aged care system requirements.
* Why we’re doing this:
	+ To create one source of information on providers and enable collaborative processes and systems within the sector.
* Who will lead it:
	+ The Department of Health and Aged Care
* Who we’ll partner with:
	+ Aged Care Quality and Safety Commission
	+ National Disability Insurance Agency
	+ Department of Veterans' Affairs
* Short-term horizon:
	+ ongoing

#### Aged Care National Minimum Data Set (NMDS)

The NMDS are national data standards for collecting and recording core aged care data. This includes data relating to people, assessments, services, providers and workers. The NMDS first version was released in 2023 and will be progressively expanded.

* What we’re going to do:
	+ finalise the scope and priorities for NMDS second version
	+ identify, define and consult on key data standards
	+ publicly release the NMDS on the AIHW GEN Aged Care Data website.
* Why we’re doing this:
	+ To improve the quality, accuracy, and consistency of national aged care data to support evidence-based decision-making.
* Who will lead it:
	+ Australian Institute of Health and Welfare
* Who we’ll partner with:
	+ Australian Digital Health Agency
	+ Aged Care Quality and Safety Commission
	+ Research organisations
* Medium-term and long-term horizon:
	+ implementation

#### National Aged Care Data Asset

The National Aged Care Data Asset will bring together information on aged care, health, and wellbeing. Its purpose is to provide a better understanding of the pathways and outcomes of people receiving aged care.

* What we’re going to do:
	+ link data about older people’s use of aged care services, health services and medicines
	+ make aged care data available to researchers through the National Health Data Hub
	+ data will be stored in a secure environment and will not include personally identifying information.
* Why we’re doing this:
	+ By bringing key datasets together, the data asset will generate insights to better identify gaps and improvements in aged care, and interactions between care sectors.
* Who will lead it:
	+ Australian Institute of Health and Welfare
* Who we’ll partner with:
	+ Aged Care Quality and Safety Commission
	+ Research organisation
* Long-term horizon:
	+ implementation

#### Aged Care Clinical Information Systems standard

Shared standards for clinical information systems used in residential aged care settings, including information coding, data structures and functional requirements.

* What we’re going to do:
	+ conduct environment scan of digital health an standards to identify existing and emerging standards for use in aged care
	+ publish recommended minimum system requirements for clinical information systems to incorporate into their product roadmaps
	+ establish an implementation roadmap of clinical information standards in aged care.
* Why we’re doing this:
	+ Improve clinical safety, enhance care co-ordination, and drive better interoperability between different systems and applications.
* Who will lead it:
	+ Australian Digital Health Agency
* Who we’ll partner with:
	+ Aged Care Quality and Safety Commission
	+ Research organisations
* Short-term horizon:
	+ work commenced

Action plan and progress for outcome 4

**Modern data and digital foundations underpin a collaborative, standards-based care system that is safe and secure.**

Progress against this outcome involves the establishment of key system-wide technical foundations to uplift the data and digital maturity and capability of the sector.

## Description of the priority areas to achieve this outcome:

Priority 7: Build and embed data and digital maturity

This priority is about improving the data and digital skills of the aged care sector to effectively manage data and use digital technologies securely. It focuses on establishing foundational technologies, frameworks and capabilities upon which the sector can develop stronger digital tools.

The aim is to create a future where the aged care sector can manage data responsibly, harness technology effectively, and where older people benefit from more efficient care.

Priority 8: Encourage innovation and provide stewardship

This priority is about government leading the way, setting guidelines and standards to ensure uniformity in the aged care sector. It recognises the need for a single, clear target for the future that the sector can work towards together.

The aim is to develop standards and frameworks that facilitate effective and unified digital innovation and adoption, promoting:

* transparency
* accountability
* optimal use of digital technologies to strengthen decision making.

## Actions linked to priorities and progress for outcome 4

### Priority 7: Build and embed data and digital maturity

#### Business to Government connectivity

Business to Government (B2G) enables streamlined reporting directly from provider to government systems.

* What we’re going to do:
	+ develop a catalogue of application programming interfaces (APIs) and use cases that allow information to be automatically reported to government including the 24/7 registered nurse responsibility and quality indicators.
* Why we’re doing this:
	+ Increase the efficiency and accuracy of information from service providers to government, allowing more time to provide direct care to older people.
* Who will lead it:
	+ The Department of Health and Aged Care
* Who we’ll partner with:
	+ Technology vendors
	+ Australian Digital Health Agency
* Short-term horizon:
	+ ongoing

#### Discovery into provider digital adoption and uplift

The technical skills and use of digital tools vary greatly among providers. We plan to improve these skills, helping those who are less experienced to use technology more effectively. This will allow providers that are already skilled to use their abilities to deliver higher quality, technology-supported care.

* What we’re going to do:
	+ establish a framework for assessing provider digital maturity
	+ assess baseline maturity levels across the sector, and determine appropriate supports
	+ establish maturity target levels, and a service catalogue for supporting uplift in specific areas
	+ explore funding and incentive models to promote maturity.
* Why we’re doing this:
	+ To have an effective and consistent aged care system, we need to use technology and data to enhance care. This requires those who provide care to be digitally mature.
* Who will lead it:
	+ The Department of Health and Aged Care
* Who we’ll partner with:
	+ Peak bodies
	+ Australian Digital Health Agency
* Medium-term horizon:
	+ planning

#### Interoperability and reference architecture

We will develop a reference architecture showing how data flows through the aged care system. It will show the systems used to capture, transfer and store this data. This includes mapping the data connection points to the health sector and other care sectors.

* What we’re going to do:
	+ overlay existing care service model with digital systems and key connection points
	+ develop journey maps for key sector personas and major data flows
	+ create current state and target systems architectures
	+ create summary reference architectures for user groups across the sector.
* Why we’re doing this:
	+ To make it clear what systems and architecture are being used in the sector. We want to provide certainty about longer-term technology investments and planned directions.
* Who will lead it:
	+ The Department of Health and Aged Care
* Who we’ll partner with:
	+ Australian Digital Health Agency
	+ Services Australia
	+ Aged Care Quality and Safety Commission
* Long-term horizon:
	+ planning

### Priority 8: Encourage innovation and provide stewardship

#### Artificial Intelligence (AI) and innovation frameworks

Emerging technologies, including AI, have the potential to increase efficiency, improve care, and lead to better outcomes for older people.

* What we’re going to do:
	+ review existing evidence and research regarding the safe and effective use of AI
	+ evaluate existing guidelines and guidance for implementing and leveraging AI
	+ investigate risks and relevant controls for deploying AI solutions
	+ adopt government guidelines for safe, controlled trials and pilots of emerging solutions
	+ promote trials and pilots in promising areas.
* Why we’re doing this:
	+ Stakeholders are asking for advice on how to safely and properly use emerging technologies, like AI, in aged care. They want to take advantage of these technologies and understand their risks and advantages.
* Who will lead it:
	+ The Department of Health and Aged Care
* Who we’ll partner with:
	+ Australian Digital Health Agency
	+ Peak bodies
	+ Digital Transformation Agency
	+ The Department of Industry, Science and Resources
* Medium-term horizon:
	+ planning

#### Artificial intelligence technology pilots in aged care

Multiple pilots would explore the potential of an AI-supported process to streamline data capture and look at ways to harness AI in aged care.

* What we’re going to do:
* Develop a number of pilots, including one that will:
	+ design a technology application and process
	+ pilot with up to 20 health professionals
	+ report on the system metrics and responses highlighting any improvements and opportunities, including the possibility of a larger scale trial with aged care workers.
* Why we’re doing this:
	+ To explore the potential of AI in providing better information and improve aged care services.
* Who will lead it:
	+ The Department of Health and Aged Care
* Who we’ll partner with:
	+ Independent Living Assessment
	+ Health professionals
	+ Technology vendors
	+ Service providers
* Short-term horizon:
	+ planning

#### Virtual reality trials in aged care

Multiple trials would explore the potential of virtual reality to improve aged care service delivery.

* **What we’re going to do:**
* evelop a number of pilots, including one that will:
	+ design an educational platform for assisted technology
	+ 20 occupational therapists to trial virtual reality
	+ evaluate the trial and report on findings and recommendations to use virtual reality for other purposes across aged care.
* **Why we’re doing this:**
	+ The trials aim to improve understanding of the practical application and effectiveness of virtual reality in aged care.
* **Who will lead it:**
	+ The Department of Health and Aged Care
* **Who we’ll partner with:**
	+ Independent Living Assessment
	+ Occupational therapists
	+ Service providers
	+ Technology vendor
* **Short-term horizon:**
	+ planning

# Delivering and developing the Plan

We are committed to delivering the Plan and each of its Actions, iteratively and collaboratively. We want to work with you on designing, implementing, and delivering all actions to make sure they’re practical and take account of realities on the ground.

We’ll use existing forums, including the Sector Reference Group, Consumer Reference Group, Tech Talks, and sector partnerships to share and discuss new initiatives. We want your input on our actions, insights on opportunities, and feedback on our progress.

**With your feedback and contributions, the Plan will be reviewed and updated regularly, outlining:**



To keep track of the Strategy's progress, we’ll use various measures to check and assess each outcome. The measures and methodologies we will use to monitor the Strategy are provided on the next page.

If you have any comments on our progress, want to help shape our actions, or have ideas for future plans, please email us at: DigitalReformStrat@health.gov.au

# Key indicators and rationales to monitor the Strategy

The below is a transcript of an infographic displaying each of the 4 strategy outcomes with the corresponding key indicators, methods and rationale that will be use to monitor its progress.

## Outcome 1:

Older people and their support networks can navigate and actively participate in their care and wellbeing.

* **Indicator:** older people’s digital and health literacy score
	+ **Method and rationale:** develop a digital literacy index in order to monitor how the literacy of older people changes over time.
* **Indicator:** number of users for key digital channels (My Aged Care, LiveUp, Be Connected, other developments)
	+ **Method and rationale:** to understand the level of uptake and use of key digital channels in this strategy.
* **Indicator:** percentage of users satisfied with engagements via digital channels
	+ **Method and rationale:** an indicator of how user-friendly, accessible and useful key digital channels are.

## Outcome 2:

Aged care workers, service providers and health professionals are digitally empowered to provide higher quality and better-connected care.

* **Indicator:** worker digital literacy scoring
	+ **Method and rationale:** develop a digital literacy index to track how the literacy of the workforce changes over time.
* **Indicator:** provider digital maturity assessment
	+ **Method and rationale:** develop a provider digital maturity assessment tool to track the digital capabilities of providers over time.
* **Indicator:** number of automated data pipelines developed
	+ **Method and rationale:** an indicator of the degree of digital connectivity and an estimate of the time re-directed to provide care.

## Outcome 3:

Data is shared and reused securely to deliver a sustainable and continually improving aged care system.

* **Indicator:** establish time saved through data integration
	+ **Method and rationale:** for each new data integration, the time saved for each transaction will be estimated.
* **Indicator:** percentage of people reporting having provided the same information in multiple places
	+ **Method and rationale:** an indicator of the degree to which we have achieved the ‘Tell us once’ principle.
* **Indicator:** percentage of systems implementing minimum data set and clinical information standards
	+ **Method and rationale:** an indicator of the consistency and capacity for interoperability in data across the sector.

## Outcome 4:

Modern data and digital foundations underpin a collaborative, standards-based care system.

* **Indicator:** number of reported data governance breaches
	+ **Method and rationale:** an indicator of the implementation and utilisation of a data governance framework.
* **Indicator:** system security maturity assessment
	+ **Method and rationale:** a security assessment tool, like Essential 8, to be used to monitor the cybersecurity maturity of key entities across the sector.
* **Indicator:** number of digital innovation pilots underway
	+ **Method and rationale:** an indicator of the effectiveness of the Strategy and innovation framework in promoting digital innovation initiatives.