# Registry Establishment Cost Drivers

# Determine the scope.

Consider including the following roles when determining the scope of the registry:

Senior Manager Registry Science

Head of ICT

Strategic Director Registry

Senior Statistician

  - Hours will vary based on the request and the role each person plays

# Build the platform.

Determine the complexity of the registry and its requirements

Discuss this with the Head of ICT to evaluate the best solution

Ensure there is adequate budget allocated for the build and ongoing maintenance

Consider the following options

- Option 1 – REDCap

Most organisations have a free licence to use REDCap however; there may be costs associated with custom builds and hosting.

As an indication a recent build for a simple REDCap Registry is around $50,000. (Not including clinician data entry and follow-up).

**NOTE: time and cost will vary based on complexity

Option 2 - Other/bespoke

Can include external ICT companies

May require internal server hosting and ongoing ICT support including secure data storage

Bespoke would need to be determined

** NOTE: Time and costs would need to be determined

# Staffing.

Registry roles may include:

- Strategic Director

Steering Committee participation governance oversight

Senior Manager Registry Science

Registry Science Oversight

Registry Project / Registry Manager

Project management/operations

Staff management and professional development oversight of ethics and governance, Stakeholder engagement of clinicians + data collections sites, Profile/promotion, budget, funding, risk management.

Ethics Officer

HREC and site governance depending on number of sites and if FQAA (Federal Qualified Privilege) sought/achieved.

Administration Officer

Research/Publication Officer

Optional or maybe required once the registry is mostly established

Data Officer / Data Manager

Data Structure and collection

Analytics Design

Senior Statistician

During the build phase and ongoing is critical to success.

Analytics and reporting

Principal Investigator / Clinician Researcher (variable)

Can be voluntary, part of the organisation or paid role

# Corporate Infrastructure.

These will be organisation specific but could include Charges are specific to each organisation HR, ICT, Finance, Insurances, Legal and Marketing in addition to office space, office expenses, ICT maintenance and support etc

# Licencing and other costs.

This may include licences such as R Studio or Power BI

This resource has been developed by the South Australian Health and Medical Research Institute Registry Centre with funding provided by the Australian Department of Health, Disability and Ageing through the National Clinical Quality Registry Program.

For further details or feedback contact registrycentre@sahmri.com

Publication Details

Publication Title: Clinical Quality Registry Establishment Cost Drivers. Published: 2025 Publisher: South Australian Health and Medical Research Institute https://doi.org/10.58138/935s-sm66

Suggested Citation

Clinical Quality Registry Establishment Cost Drivers. South Australian Health and Medical Research Institute. June 2025. Version 1. https://www.health.gov.au/resources/publications/registry-establishment-cost-drivers

Copyright

Except as otherwise stated, all material is © South Australian Health and Medical Research Institute Limited.

All material presented in this publication is provided under a Creative Commons Attribution NonCommercial-NoDerivatives

4.0 International Licence (www. creativecommons.org.au), with the exception of all images (including background images, logos and illustrations) and any content identified as being owned by third parties. The details of the relevant licence conditions are available on the Creative Commons website (www.creativecommons.org.au), as is the full legal code for the CC BY-NC-ND 4.0 International Licence https://creativecommons.org/licenses/by-nc-nd/4.0/deed.en

Attribution

Creative Commons Attribution NonCommercial-NoDerivatives 4.0 International Licence is a standard licence agreement that allows you to copy and distribute this publication provided that you attribute the work, do not use the material for commercial purposes and do not distribute modified work.

SAHMRI requests that you attribute this publication (and any material sourced from it) by using the following wording: Source: South Australian Health and Medical Research Institute.

Use of Images

Unless otherwise stated, all images (including background images, logos, icons and illustrations) are copyrighted by their original owners.