## Slide 1
IMPLEMENTATION TIMELINE
Phase 1 – Prepare (June – September 2026) |  |  |  |  |  |  | Phase 2 – Implement(October – December 2026) |  | 
 | Jun | Jul | Aug | Sep | Sep late | 1 Oct | Oct | Nov | Dec
1. Understand, build awareness, brief stakeholders |  |  |  |  |  |  |  |  | 
2. Prepare participants |  |  |  |  |  |  |  |  | 
3. Prepare organisation & workforce |  |  |  |  |  |  |  |  | 
4. Prepare ICT & systems |  |  |  |  |  |  |  |  | 
5. Apply the change |  |  |  |  |  |  |  |  | 
6. Resolve and monitor |  |  |  |  |  |  |  |  | 
 |  |  |  |  | Final checks | Go live |  |  | 
Support at Home – Personal Care Contribution Change
Go-live 1 October 2026
Awareness and foundations
Apply and monitor
Active implementation
Read, brief, subscribe and attend provider information sessions
Outreach and comms
Review business processes
Confirm system changes
Discuss care plans
Update budgets and service agreements
Plan for participant demand changes
Update documentation
Train and prepare staff
Final checks
Configure
Test
Go-live ready
Manage participant enquiries
Reinforce new ways of working
Embed ICT and systems changes
Apply change
Close out
About this guide | How to use this guide | For support
This guide supports registered Support at Home providers delivering personal care services to prepare for the personal care contribution changes taking effect from 1 October 2026. From 1 October, all personal care services under the Support at Home service list will move from the Independence contributions category to the Clinical Supports contribution category. This is a mandatory change for all registered providers delivering personal care under Support at Home. | This guide is designed for providers of different sizes, systems and service delivery models. It is intended to be used alongside the online Provider Readiness Checklist. Use this guide to support planning, implementation and monitoring activities for the personal care contribution change. | For implementation support: email SAH.implementation@health.gov.au to join the Support at Home Community of Practice, email SAH.implementation@health.gov.au subscribe to Your Aged Care Update (YACU) at aged care newsletters and alerts For support with claiming, contact the Services Australia Aged Care Provider Line 1800 195 206
Reinforce key messages
Monitor and resolve issues

## Slide 2
Phase 1 - Prepare | 1. Understand, build awareness, brief stakeholders | 2. Prepare participants | 3. Prepare organisation and workforce | 4. Prepare ICT & systems
 | 1.1 Understand and communicate the change | 2.1 Prioritise participant outreach | 3.1 Review and update business processes | 4.1 Confirm system changes with ICT teams and/or software vendors
 | 1.2 Engage your ICT team and/or software vendor | 2.2 Communicate the change to all participants | 3.2 Update documentation and templates | 4.2 Monitor vendor readiness and ICT related risks
 | 1.3 Identify affected participants | 2.3 Engage with participants to discuss their care plans | 3.3 Update billing and finance processes | 4.3 Update system configuration
 | 1.4 Subscribe to updates, stay informed and communicate changes | 2.4 Update individual participant budgets | 3.4 Ensure alignment across care plans, service agreements and billing | 4.4 Update and test connected systems and outputs
 | 1.5 Attend information sessions for providers | 2.5 Engage with participants to review and update service agreements | 3.5 Train and support staff | 4.5 Confirm system readiness for go-live
 |  | 2.6 Plan for workforce impacts and changes in participant demand | 3.6 Prepare staff for the transition period | 
Phase 2 - Implement | 5. Apply the change | 6. Resolve and monitor performance | Key online resources | 
 | 5.1 Apply the new contribution settings from 1 October | 6.1 Monitor billing, claiming and reporting for accuracy | Use the following resources to guide implementation: Personal Care Contribution Change Provider Readiness Checklist Department web page for providers: Personal care contribution change My Aged Care web page for older people: Personal care to be fully funded under Support at Home from October Support at Home program manual – A guide for registered providers Support at Home eLearning for aged care providers Support at Home service list For software developers access the Health Systems Developer Portal for integrated software related information. | 
 | 5.2 Manage participant enquiries | 6.2 Monitor demand and service delivery |  | 
 |  | 6.3 Resolve outstanding issues and close out the transition |  | 
 |  | 6.4 Conduct a post implementation review to identify lessons learned |  | 
Support at Home – Personal Care Contribution Change
Go-live 1 October 2026
READINESS CHECKLIST SUMMARY ACTIONS