## Slide 1: Personal care information sessions for Support at Home providers
Pull quote
17 September 2026

## Slide 2: Acknowledgement of Country
We would like to acknowledge the Traditional Owners and Custodians of the lands on which we meet today and pay my respects to Elders past, present and emerging.
We would like to extend that acknowledgement and respect to any Aboriginal and Torres Strait Islander peoples here today.

## Slide 3: Housekeeping
Session purpose: To highlight final preparations for the changes to personal care contributions on 01 October.
Q&A at the end of the session
Please raise your hand to ask a question
Questions will be taken verbally only — chat is disabled
Poll at the end of the session to get your feedback
In scope
Operational matters following the recent announcement of the personal care contribution changes coming into effect on 1 October 2026.
Out of scope
Changing policy and legislative settings agreed by Government and articulated in the Aged Care Act.

## Slide 4: Session 8 recap
Theme | What we heard | What we are doing
Final readiness and implementation progress | Providers are focused on completing, testing and confirming readiness activities before 1 October, including participant communications, documentation, business processes and system changes. | Reinforced the Provider Readiness Checklist and guided providers through the final actions, testing activities and readiness checks required before implementation.
Participant readiness and communication | Providers are continuing participant outreach and preparing for participant enquiries as implementation approaches. | Released the Easy Read resource, promoted the Stakeholder Kit for Providers, highlighted available communication supports and resources, and planned departmental communication to older people during September.
Systems, workforce and operational readiness | Providers are focused on end-to-end testing, staff readiness and resolving any outstanding ICT or software vendor issues ahead of go-live. | Continued guidance on workforce preparation, documentation alignment, system testing and escalation pathways for implementation risks and vendor delays.
Go-live and post-implementation activities | Providers are beginning to focus on what happens after 1 October, including billing, participant enquiries, monitoring and issue resolution. | Highlighted post-implementation activities, including monitoring billing and claiming outcomes, participant statements, service demand and workforce impacts.
Engagement and ongoing support | Providers continue to value direct access to implementation support and opportunities to raise readiness questions and risks. | Continued provider information sessions, promoted support channels and encouraged providers experiencing implementation issues to contact the Support at Home implementation team.

## Slide 5: Timeline
Apr 26
Sector announcement of Personal Care contribution changes
May 2026
Early sector engagement:
ACSWG, industry peaks
Software vendor initial engagement and Tech Talks
Jun – Sep 2026
Targeted consultation and transition support:
Provider readiness survey
Provider information sessions
Ongoing engagement via ACSWG industry peaks, software vendor/developer engagement (Services Australia) and Tech Talks
Provider readiness checklist and guidance
Communication materials progressively released.
Aug – Sep 2026
Finalise, test and confirm readiness:
Finalised system changes
Final sector pre-go-live communications
Readiness checks
1 Oct 2026 Go-live. Personal Care moves to Clinical Supports contribution category.
Oct – Dec 2026
Post-implementation support and monitoring.

## Slide 6: Implementation support
Provider Readiness Checklist
Stakeholder Kit for Providers
Department web page
My Aged Care web page
How to get support:
Support at Home implementation support: SAH.implementation@health.gov.au
Support at Home Community of Practice: join by emailing SAH.implementation@health.gov.au
Your Aged Care Update (YACU): Subscribe for aged care news, resources and updates
Claiming support: Services Australia Aged Care Provider Line 1800 195 206

## Slide 7: Critical scenarios to avoid
Pull quote

## Slide 8: Older person/supporter
Overall goal: understand the change, continue to receive the care they need, and can make informed decisions about their services and costs.
Ideal participant experience | I am aware a change is coming and know where to get information | I understand what is changing, what is not changing and what it means for me | I am confident my care arrangements and documentation accurately reflects the change | I continue to receive care as planned and the change does not disrupt my services | I can understand my monthly statement, charges and any contributions that still apply | I receive the care I need and can make informed decisions about my services
Touchpoint | I receive clear information about the change, when it will happen and where I can go with questions | My care partner explains how the change affects my personal care, costs and existing services and answers my questions | My care plan, budget and service information are updated and consistent | I receive approved personal care and do not pay a contribution for personal care for services delivered after 1 October | My monthly statement clearly explains my services, charges and any contribution that still applies | My provider gives me accurate information and keeps my care arrangement current as my needs change
Artefacts/ information | Provider issued communication Provider issued letters/emails Provider website information Fact sheets | Information on My Aged Care or Health website. Advice from family, carers or advocacy organisations | Care plan Individual budget Service agreement (if required) Pricing information | Updated service arrangements | Participant monthly statement | Care plan review Budget discussion Changes to service use Ongoing conversations with provider
Provider critical scenarios to avoid | 1. Frontline staff cannot explain the change consistently 2. Some participants (which may include including CALD and First Nations) do not understand the change or how it affects them | 3. Participant receives conflicting information about the change reducing confidence in their understanding of the change 4. Participant believes approval, eligibility or funding limits no longer apply and expects services beyond their approved care arrangements | 5. Participant receives conflicting information across their care documentation (care plans, budgets, service agreements, examples) | 6. Participant is charged a personal care contribution after 1 October | 7. Participant believes the removal of personal care contributions applies to services delivered before 1 October 8. Participant does not understand why charges or contributions still appear on their monthly statement after 1 October | 9. Participant does not understand how the change affects their costs, services or available funding 10. Participant cannot understand why some services in the same visit attract a contribution and others do not 11. Participant expects additional services, but does not have available funding 12. Participant expects additional services but provider capacity cannot meet demand
Key participant questions | What is changing? When will the change happen? Where can I get more information? | What does this mean for me? Will my services change? Will I still need to pay for any services? | Are my care arrangements correct? Why have these documents changed? Do I need to do anything? | Has anything changed for my care? Am I still receiving the same services? Am I being charged correctly? | Why am I receiving a bill? Why do some charges still appear on my monthly statement? Why do some services have a contribution and others do not? | What personal care can I access? How do costs affect my budget and services? How do I change my services if my needs change?
Prepare for change
Understand the change
Receive updated documents
1 October go-live
First invoice/participant statement
Ongoing care & review
Focus: Go-live and October implementation

## Slide 9: Key actions for go-live and October
Apply the correct billing treatment.
Participants should not be charged a personal care contribution for services delivered from 1 October.
Explain the change consistently.
Participants should understand what has changed, what has not changed, and where to get help.
Support participant questions and requests.
Be prepared to explain statements, available funding, service options and capacity constraints.

## Slide 10: 1. Question and Answer
Regarding the Department’s webpage - when will the Support at Home service list be updated to reflect personal care services under the clinical support category?
On 1 October, a new version will be published with personal care services under clinical supports. The department will shortly upload an interim version that notes the upcoming change in category.
?

## Slide 11: 2. Question and Answer
Regarding the Department’s webpage - Funding for Support at Home aged care nurses’ award wage increase – when will this be updated to include Transitioned HCP Level 1-4 budgets?
Rates for all ongoing classifications, including transitioned classifications, will be updated shortly in the Schedule of Subsidies and Supplements for Support at Home.
?

## Slide 12: Questions?
Asking questions
Please raise your hand to ask a question.
Please identify yourself when speaking - your first name and organisation is sufficient.
Answering Questions
Our team are here to help you
Some questions may need to be taken on notice to follow up out of session.

## Slide 13: Check your implementation readiness

## Slide 14: We'd love your feedback
Please complete our short poll.
More to say? Reach out to: SAH.implementation@health.gov.au
Thank you

## Slide 15: Check your implementation readiness
Pull quote

## Slide 16: 1. Understand, build awareness and brief stakeholders
1.1 Understand and communicate the change
COMPLETE
1.2 Engage your ICT team and/or software vendor
COMPLETE
1.3 Identify affected participants
COMPLETE
1.4 Subscribe to updates, stay informed and communicate changes
COMPLETE
1.5 Attend information sessions for providers
COMPLETE
POINTS TO NOTE:
Continue to communicate the change with all stakeholders
Stakeholder Kit for Providers is now available
Confirm readiness activities have clear owners and delivery dates
Continue monitoring updates through health.gov.au, My Aged Care and the Community of Practice
Provider information sessions continue – use them to resolve implementation questions and risks
Have we completed the actions required to support implementation on 1 October?
KEY QUESTION:

## Slide 17: 2. Prepare participants
2.1 Prioritise participant outreach
COMPLETE
2.2 Communicate the change to all participants
COMPLETE
2.3 Engage with participants to discuss their care plans
FINALISE NOW
2.4 Update individual participant budgets
FINALISE NOW
2.5 Engage with participants to review and update service agreements
FINALISE NOW
2.6 Plan for workforce impacts and changes in participant demand
FINALISE NOW
POINTS TO NOTE:
Complete priority participant outreach.
Finalise participant communications before go-live.
Complete required care plan, budget and service agreement updates.
Confirm additional communication support for participants who need it.
Prepare for possible changes in personal care demand.
Have affected participants received clear information, and will their care plans, budgets and agreements be accurate from 1 October?
KEY QUESTION:

## Slide 18: 3. Prepare organisation and workforce
3.1 Review and update business processes
COMPELTE
3.2 Update documentation and templates
FINALISE NOW
3.3 Update billing and finance processes
FINALISE NOW
3.4 Ensure alignment across care plans, service agreements and billing
FINALISE NOW
3.5 Train and support staff
FINALISE NOW
3.6 Prepare staff for the transition period
FINALISE NOW
POINTS TO NOTE:
Complete end-to-end process updates.
Finalise participant-facing documents and templates.
Confirm pre- and post-1 October billing treatment.
Conduct a sample quality check across care plans, agreements and billing outputs.
Complete staff training and provide transition scripts, FAQs and scenarios.
If the change went live tomorrow, would your staff, processes, documents and billing arrangements produce a consistent and accurate outcome?
KEY QUESTION:

## Slide 19: 4. Prepare ICT & systems
4.1 Confirm system changes with ICT teams and/or software vendors
COMPLETE
4.2 Monitor vendor readiness and ICT related risks
FINALISE NOW
4.3 Update system configuration
FINALISE NOW
4.4 Update and test connected systems and outputs
FINALISE NOW
4.5 Confirm system readiness for go-live
FINALISE NOW
Have your systems been configured and tested end to end, and can you demonstrate that they will apply the correct treatment on each side of 1 October?
POINTS TO NOTE:
Confirm final vendor delivery dates.
Complete configuration across all affected systems.
Test services delivered before and from 1 October.
Test invoices, statements, billing, claiming and reporting outputs.
Resolve defects or formally assess and escalate remaining risks.
Confirm there is no reliance on unapproved manual workarounds.
Have your systems been configured and tested end to end, and can you demonstrate that they will apply the correct treatment on each side of 1 October?
KEY QUESTION:

## Slide 20: 5. Apply the change
5.1 Apply the new contribution settings
FROM 1 OCTOBER
5.2 Monitor participant enquiries
FROM 1 OCTOBER
FOR IMPLEMENTATION SUPPORT
email SAH.implementation@health.gov.au
to join the Support at Home Community of Practice, email SAH.implementation@health.gov.au
subscribe to Your Aged Care Update (YACU) at aged care newsletters and alerts
for support with claiming, contact the Services Australia Aged Care Provider Line 1800 195 206
POINTS TO NOTE:
Do not apply participant contributions to personal care delivered from 1 October.
Continue to apply the relevant treatment to services delivered before 1 October.
Check billing, claiming and participant statements.
Ensure frontline staff can respond to participant questions.
Record recurring questions and provide additional guidance where needed.
Are your people and systems ready to apply the correct treatment from day one and respond consistently to participant questions?
KEY QUESTION:

## Slide 21: 6. Resolve and monitor performance
6.1 Monitor billing, claiming and reporting:
FROM 1 OCTOBER
6.2 Monitor demand and service delivery
FROM 1 OCTOBER
6.3 Resolve outstanding transition issues
FROM 1 OCTOBER
6.4 Conduct a post implementation review
FROM 1 OCTOBER
POINTS TO NOTE:
Review early billing, claiming and participant statement outputs.
Correct errors promptly and escalate recurring system issues.
Monitor changes in personal care demand and workforce capacity.
Complete outstanding participant record and agreement updates.
Capture lessons from implementation.
What will you monitor after go-live, who will review the information, and how will issues be escalated and resolved?
KEY QUESTION: