## Slide 1: Wellness and REABLEMENT CHANGE MANAGEMENT PLAN
FOR
STEP BY STEP GUIDE

## Slide 2: INTRODUCTION: PURPOSE AND AUDIENCE
The purpose of this change management plan is to assist Commonwealth Home Support Programme (CHSP) service providers in embedding Wellness and Reablement (W&R) within their organisation and delivering W&R services to clients in the aged care sector.
The change management plan is designed as a practical tool for service provider management teams to plan and undertake change activities in their organisation. This document includes the following:
Section 1 – Introduction to change management and why it is important.
Section 2 – Step by Step Change Management Plan
A change management plan helps facilitate, capture and formalise the various change discussions and activities that your team may be undertaking. It allows you to capture and share the change goals, approach, activities and deliverables across your organisation. It can then be used to track, measure, adjust and communicate the status of the change management activities across your organisation.
NOTE: The change management plan can be used in conjunction with your organisation's Quality Improvement Plan, if you already have one.
2

## Slide 3: Section 1:
Introduction
This section provides an introduction on what is change management and why it is important.

## Slide 4: WHAT IS CHANGE MANAGEMENT?
4
Change management helps people make a personal transition from a current to a future state. It ensures the organisation is ready, willing, and able to function in the new environment, the desired business benefits are realised, and that the transition process to the end state is as smooth as possible.
Change management follows a repeatable process and applies holistic tools and techniques to manage the people side of change to achieve the required business results. If done effectively, change management also assists in addressing project risks by clearly defining remediation strategies to minimise adverse business impacts (often in the form of resistance).
1Source: Prosci Best Practice Change Management Report 2017

## Slide 5: WHAT IS CHANGE MANAGEMENT?
Change management increases the likelihood of a project’s success by working to ensure individuals in the organisation embrace and adopt changes (see Figure 1). Initiatives with excellent change management are approximately 6 times more likely to meet objectives than those with poor change management.
Change management specific to this project is important to further drive service provider staff delivering services with wellness and reablement (W&R) as a core objective.
Figure 1. Effectiveness of change management on projects
1Source: Prosci website
PERCENT OF PROJECTS THAT MET OBJECTIVE
POOR CHANGE MANAGEMENT
FAIR CHANGE MANAGEMENT
GOOD CHANGE MANAGEMENT
EXCELLENT CHANGE MANAGEMENT
15%
42%
76%
94%
5

## Slide 6: WHY COMPLETE A CHANGE MANAGEMENT PLAN?
A change management plan helps formalise and capture the various change discussions and activities that your team may be undertaking. It allows you capture and share the change goals, approach, activities and deliverables across your organisation.
It can then be used to track, measure, adjust and communicate the status of the change management activities across your organisation.
6

## Slide 7: Section 2:
This section provides a practical process to systematically identify and capture change activities within your organisation. It also provides a change management template and example to help you get started.
STEP BY STEP CHANGE MANAGEMENT PLAN

## Slide 8: STEP 1 – IDENTIFY CHANGE GOALS
It is important to identify the change we are making and why we are making this change. Key points to consider:
Why is the change important at all levels of your organisation?
Why is it important to the survival and growth of your organisation?
Why is it important to the wellness of your customers and clients?
Why is it important to the work of your support workers?
Why is it important to your support workers, especially their job satisfaction?
What are some news stories you would like to see your organisation featured in the media? E.g. Would you like to be featured in a positive story of how some service providers are actively assisting clients become more independent?
The ‘More Good Days’ Toolkit provides additional guidance on setting the right goals for your organisation.
Identify change goals
Document your change activities
Identify how you will measure your success
Identify how you will achieve the change
Identify what needs to change
STEP 1
STEP 2
STEP 3
STEP 4
STEP 5
8

## Slide 9: STEP 2 – IDENTIFY WHAT NEEDS TO CHANGE
Once you have defined the change and its objectives, the next step is to identify what needs to change. We need to look at how this change will impact on the current way of doing things across People, Process and Systems. Key questions to ask:
PEOPLE
Will this change require our people to work differently?
Will they need to adjust their attitudes?
Will they need to acquire new skills?
Will we need to change the team structures and reporting lines to adapt to this change?
PROCESS
Do our standard operating procedures and processes need to change?
Do our policies need to change?
Do our reporting processes / metrics need to change?
SYSTEMS
Do we need to update our systems or implement new systems to enable the change?
Does content on our systems (internet / intranet / wiki) needs to change?
Identify change goals
Document your change activities
Identify how you will measure your success
Identify how you will achieve the change
Identify what needs to change
STEP 1
STEP 2
STEP 3
STEP 4
STEP 5
9

## Slide 10: STEP 3 – IDENTIFY HOW YOU WILL ACHIEVE THE CHANGE
Once we have identified what needs to change, we need to think of ways to enable the change and achieve our change objectives. Some proven methods include:
TRAINING & COACHING
What training and coaching do we need to provide our people to adopt the change? Is it only technical training or does it also need to include training in soft skills?
Can we setup a community of practice or participate in an existing one?
PROCESS IMPROVEMENTS
How do we change the processes, policies and procedures to facilitate the change?
TARGETED COMMUNICATIONS
What communications can we develop to help people understand and embrace the change?
What channels can we use?
Rewards & Recognition
Can we use rewards and recognition to inspire people to adopt the change?
Identify change goals
Document your change activities
Identify how you will measure your success
Identify how you will achieve the change
Identify what needs to change
STEP 1
STEP 2
STEP 3
STEP 4
STEP 5
The ‘More Good Days’ Toolkit provides useful material to help you quickly develop change management and communications products, and accelerate the uptake of wellness & reablement within your organisation.
10

## Slide 11: STEP 4 – IDENTIFY HOW YOU WILL MEASURE YOUR SUCCESS
Once you have defined the goals and the key change management tools that you will employ to achieve your change goals, it is time to develop key metrics to measure performance over time. This will help you understand how effective your change management approach and activities are in achieving your change goals, and to help you shape and improve them.
Ideally, you want to measure progress against high level goals such as:
What client wellness and reablement benefits are you delivering?
How has client satisfaction changed over time (e.g. NPS score tracking over time)
The above can take time to realise and may be hard to measure. It is equally useful to have activity based / lower level measurements such as:
What percentage of staff have undertaken training?
What percentage of clients are setting reablement goals?
Do you have ability to record and measure client outcomes?
Is your organisation accepting a majority of short-term reablement referrals?
Identify change goals
Document your change activities
Identify how you will measure your success
Identify how you will achieve the change
Identify what needs to change
STEP 1
STEP 2
STEP 3
STEP 4
STEP 5
The ‘More Good Days’ Toolkit > CHSP Responsibilities section provides a useful survey that could be used to baseline and measure success over the course of your organisation’s change journey.
11

## Slide 12: STEP 5 – DOCUMENT YOUR CHANGE ACTIVITIES
As you work through the change management steps, you will start to form a picture of what needs to change and how you will enable the change.
It is important to document the discussions from the change manage steps into a cohesive and structured plan. This will help you further clarify your thinking, and provide a formal and shared view of your change approach and activities.
It is critical that a executive level change sponsor and a more operational level change manager is identified to be accountable for driving the change in your organisation.
To assist you with implementing W&R in your organisation, a Change Management Plan has been developed, providing a high level template to help you capture your findings in a structured and cohesive document.
Sample answers have also been provided to assist you in completing it quickly and effectively. It is important that you use the sample answers as a guideline, and adapt them to your organisation and situation.
Identify change goals
Document your change activities
Identify how you will measure your success
Identify how you will achieve the change
Identify what needs to change
STEP 1
STEP 2
STEP 3
STEP 4
STEP 5
12

## Slide 13: CHANGE MANAGEMENT PLAN ON A PAGE
Change Team |  |  | 
Change Sponsor |  | Change Manager | 
Change Objectives
What Needs to Change
Change Approach – How we will get there
Measures of success |  | 
Measure | Current | Target
 | 0% | 100%
High Level Delivery Timeframe |  | 
Activity | Start Date | End Date
13

## Slide 14: CHANGE MANAGEMENT PLAN ON A PAGE (Content below is for guidance only)
Change Team |  |  | 
Change Sponsor |  | Change Manager | 
Change Objectives
1 - Embed wellness and reablement into our services
2 - TBA
What Needs to Change
People – The following teams / roles will need to adjust their mindset, skills and behaviours to achieve the change objective: Support workers need to be educated on wellness and reablement philosophy Support workers need to be trained on how to educate clients on wellness and reablement, and deliver services to support the client’s reablement goals
Processes – The following processes / procedures will need to be updated to facilitate the change: Client engagement and assessment process / checklist needs to be changed to be more wellness focused Team reporting process needs to include wellness & reablement metrics Employee recruitment and induction process for new starters
Systems / Technology – The following systems will need to updated or adopted to facilitate the change: Website content needs to change to reflect our focus on wellness and reablement Train staff on using the Digital Hub to find key wellness and reablement resources
Change Approach – How we will get there
Training & Coaching – Develop and deliver training to support workers using a combination of classroom and e-learning formats, and deliver ongoing coaching (See Attachment A) Community of Practice – Encourage senior support workers to participate in the Department of Health’s CoP platform (See Attachment A) Communications – Develop and deliver a series of targeted communication (See Attachment B) Rewards & Recognition – Regularly acknowledge staff who are providing client service excellence in terms of wellness & reablement (See Attachment B) Intranet & Internet Content Changes – Change the content to be more wellness and reablement focused (See Attachment B)
Measures of success |  | 
Measure | Current | Target
Number of support workers who have completed wellness & reablement training | 0% | 100%
Number of clients who have achieved their reablement goals |  | 
Team ADKAR Score (see Attachment C) |  | 
High Level Delivery Timeframe |  | 
Activity | Start Date | End Date
Develop & deliver training material |  | 
Develop & deliver comms products |  | 
Update team processes |  | 
Measure change outcome |  | 
14

## Slide 15: ATTACHMENT A - TRAINING & COACHING PLAN (Content below is for guidance only)
Group 1 – Senior Support Workers |  |  | 
Training Item | Training Type | Training Outcomes | Target Completion Date
Wellness & Reablement Fundamentals | Classroom training and e-learning | Team member understands the importance of reablement and wellness | 30 June 20XX
Wellness & Reablement Advanced | Classroom training and e-learning | Team member understands how to apply wellness in the provisioning of their services | 30 July 20XX
Participate in Digital Hub /CoP | E-engagement / e-learning | Team member is aware of how other organisations are applying wellness & reablement in their organisation | 30 June 20XX
TRAINING & COACHING APPROACH
Describe your approach to developing and delivering training and coaching activities.
E.g. we will adopt a tiered approach to training and coaching to balance depth and cost. We have identified two groups (Senior Support Workers and Support Workers). Senior support workers will be provided in-depth classroom training and will then train and coach the junior support workers on the job.
Group 2 – Support Workers |  |  | 
Training Item | Training Type | Training Outcomes | Target Completion Date
Wellness & Reablement Fundamentals | Classroom training and e-learning | Team member understands the importance of reablement and wellness | 30 June 20XX
Coaching | On-the-job learning | Team member understands how to apply wellness in the provisioning of their services | 30 June 20XX
15

## Slide 16: ATTACHMENT B - COMMUNICATIONS PLAN (Content below is for guidance only)
Key Communications Products |  |  | 
Communication Product | Channel | Frequency | Initial Target Completion Date
CEO Email on the importance of wellness & reablement | Email | Every 6 months | 30 June 20XX
Intranet & internet content changes | Online | One-off | 30 June 20XX
Ongoing intranet & internet content review | Online | Annually | NA
Team member of the month award | Email | Monthly | Ongoing
Reablement & Wellness newsletter | Email | Monthly | Ongoing
Wellness posters | Print | One-off | 30 July 20XX
Wellness and reablement lunch and learn sessions | In-person | Monthly | 30 July 20XX
Key Messages
It is critical to embed wellness & reablement into our services
Support workers are vital in understanding and delivering client wellness needs
16